## Sheet1
Module 2.3 - Visualizing the Budget - Instructions
1. Review the memos to identify updated costs, removed tasks, and any new requirements.
2. Revise the 2021 cost table with the new line items and amounts.
3. Assign costs to the appropriate dates based on your Gantt chart (e.g., deposits, permits, delivery, installation).
4. Update the cumulative totals in the table.
6. Create an updated Cost Baseline Diagram (cumulative cost curve) from your table.
7. (Bonus) Improve the diagram, highlight the key cost changes from 2021, and apply formatting that guides the viewer’s attention.
For tasks with ongoing costs (e.g., rentals, facility prep), spread the total cost evenly across their duration instead of recording it as a single lump sum at the beginning of the task
2021 Cost Table
Item Name | Cost Date | Cost | Cumulative Cost
Project Start | 2021-02-10 | 0 | 0
PaintTech EasyDry Paint Booth (Deposit) | 2021-02-27 | 25000 | 25000
Facility Inspection Fees | 2021-02-27 | 1500 | 26500
LADBS Building Permit | 2021-02-27 | 500 | 27000
LADBS Electrical Permit | 2021-02-27 | 150 | 27150
LADBS Mechanical Permit | 2021-02-27 | 150 | 27300
LADBS Plumbing Permit | 2021-02-27 | 150 | 27450
LAFD Sprinkler Permit | 2021-02-27 | 1000 | 28450
SCAQMD Permit to Construct | 2021-02-27 | 1400 | 29850
SCAQMD Permit to Operate | 2021-02-27 | 1200 | 31050
Facility Prep (Electrical, HVAC) | 2021-02-27 | 5000 | 36050
Equipment rentals (Boom lift, etc.) | 2021-02-27 | 1500 | 37550
PaintTech EasyDry Paint Booth (Remaining upon delivery) | 2021-03-28 | 25000 | 62550
Paint Booth installation | 2021-03-29 | 2000 | 64550
Sprinkler installation | 2021-04-03 | 5000 | 69550